| MEETING TITLE: | City of Seguin – Cordova Rd Reconstruction Kickoff |  | DATE: | 09/16/2022 |  |
| --- | --- | --- | --- | --- | --- |
| PROJECT NUMBER: | 12775-00 |  |  |  |  |
| AGENDA TOPICS: |  |  |  |  |
| General Project |  | - Intro and Team Members - Status of Administrative Documents - AFA - Dual logos with County? - County / Others? - Billing - Status report preference items - Invoice template or preference - Timeline - Survey – Aerial (09/17) 10/2022 - DCC – 11/2022 - 30% DDRT / Schematic – 01/2023 - 60% DDRT – 05/2023 - 90% DDRT – 08/2023 (Hold plans during ROW / Utility) - Final Plans – 12/2024 - Funding and Commitments - Budget Presentation $31M - Prelim OPCC $33M - $37M w/escalation - How is ROW calculated |  |  |
| 110 Feasibility Studies |  | - Field reconnaissance - Geotechnical - Pavement alternatives - Proposing only flexible options - Specific material preferences? - General preferences required? - Will need to estimate ESALs / Counts - Pavement Report - Drilling and site investigations - Borings in 3-4wks; 3 wks for processing draft designs - Traffic Studies - Received counts - Planned analysis / TPP vs Option C vs ESALs - Summary Report - Any template preference? |  |  |
| 120 ENV / Public Involvement |  | - ENV - TxDOT Coordination - Anticipating a CE - NEPA / ECOS - Workplan development / ENV Toolkit - Determination of 404 Permitting - ENV Coordination - Environmental impacts etc. - What ENV considerations are presently known? - Optional Assessments and Schedule - Public Involvement - Planned Meetings - Schematic phase - Design phase - Public meeting processes - ADA, location, etc - Approval of outreach materials - ROW acquisition - Schedule and regulatory timelines |  |  |
| 130 ROW Data |  | - ROW - Right of entry update - Could our team support with non-responders? - ROW mapping and deliverables - Schedule Update - Utility Coordination - Utility layouts - Utility Conflict Matrix – TxDOT Standard - Major petroleum line - NOPC – Preferred template? - Scheduled meetings; need to begin soon - Seguin specific contacts |  |  |
| 131 ROW Acquisition |  | - Uniform Act Requirements - TxDOT Forms? - Appraisal and Title require TxDOT Pre-Approved List Agent - Preparation and starting? - Development of plan framework - Integrating with Connie Real’s Team - Suggested frequency for regular meetings and coordination - Prioritization of problematic parcels - Property owner engagement / Public Involvement blending - Negotiations and timelines - Relocation assistance |  |  |
| 150 Survey |  | - No planned discussion points |  |  |
| 160 Roadway Design |  | - Preliminary Geometric Layout - 2 – design alternatives (termini at intersections) - ROW constraints / developments - DCC - LG process, DDRT / DSRT - Constraints mapping - Pedestrian and bicycle facilities - Regional expansion considerations - TxDOT RDM governed |  |  |
| 161 Drainage |  | - Data collection and field work - Design criteria and design storm - Hydrology studies and modeling requirements - Existing models - Hydraulic modeling and anticipated design - HEC-RAS and complex modeling / Hydraulic Data Sheets - Storm drain design and outfalls - Detention requirements |  |  |
| 162 Traffic |  | - TPP vs Option C - Signing – specifics? mounts? - Warrants and timing plans; specific templates requested? - Traffic signal design – TxDOT Standards - Known problem locations |  |  |
| 163 Misc Design |  | - TCP - Likely quad-phased - Lessons learned - Public Involvement strategy - SW3P - Constraints and mitigation measures - Development of CPM schedule - Anything specific required from City |  |  |
| 164 SUE |  | - No planned discussion points |  |  |
| Project Management |  | - Bi-weekly status meetings (Transition to weekly once project initiates) - Invoicing - Communication protocols - Next steps |  |  |
| Open Discussion |  |  |  |  |
| ACTION ITEMS: Description |  |  |  |  |