| PROJECT: | Cordova Rd- SH 46 to SH 123 |  | DATE: | February 10th, 2023 |
| --- | --- | --- | --- | --- |
| CONFERENCE LOCATION: |  | Virtual – Teams Meeting | CONFERENCE DATE: | February 10th, 2023 |
| PURPOSE OF MEETING: |  | ENV Status Update |  |  |
| ATTENDEES: |  | PD: John Tyler, Jake Powell, Steven Tate RKCI: Brittney Davis |  |  |
| FROM: |  | John Tyler, P.E., RAS | PROJECT NO.: | 12775-00 |

DISCUSSION:

Schedule- Current design schedule (dependent of AFA)

- DCC – 4/2022 based on TxDOT’s ability to participate due to AFA status

- 30% DDRT / Schematic – 05/2023- Full TxDOT schematic

- 60% DDRT – 09/2023- Following TxDOT procedures may require PDCC (pavement design review) and DSRT (safety review) at the 30% or 60% level.

- 90% DDRT – 112/2023 (Hold plans during ROW / Utility)- Shown as 100% in contract, plans ready to let but there will be ~14 month period for ROW acquisition, utility relocations, etc. Certification will not be ready until utilities and ROW are clear.

- Final Plans – 4/2025- 8/2025 letting, final plans 5 months prior to being let.

Project Development Updates

- ROE on-going. CoS sent project introduction letters to residents.

- SharePoint site created with ROE tracking information- Access needed?

- Initial traffic projections complete, submitted to TxDOT for review (waiting of AFA)

- Geotechnical field investigations complete, laboratory

- Topographic survey complete

- Existing ROW resolution and mapping 99% complete, final deliverable next week

- Evaluated alignment alternatives

- Development of preliminary typical sections

- Conducted geometric workshop with CoS and Guadalupe County

  - Preliminary schematic and alternatives available

TxDOT Environmental Initiation

- TxDOT ECOS documentation for TxDOT

  - What information is necessary to complete this process

  - What can be done now?

Environmental Document

- CE vs EA

  - Technical differences

  - Schedule impacts

- ROW impacts

  - Preferred alignment shown in preliminary layout has the following

    - 48 impacted parcels

    - ~24 AC of acquisition

  - Alternative of interest

    - ~33 AC

    - Potential for donation of existing ROW

- Conservation easements

  - Unknown at Big Red Barn and electrical sub-station

  - Impact to ENV document?

  - RKCI have the ability to determine conservation easements?

END OF MEMO

P:\127\75\00\ProjectData\MeetingMinutes\230210- ENV update\230210_Cordova_ENV_Status.docx