|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **PROJECT:** | Cordova Rd- SH 46 to SH 123 | | **DATE:** | February 10th, 2023 |
| **CONFERENCE LOCATION:** | | Virtual – Teams Meeting | **CONFERENCE DATE:** | February 10th, 2023 |
| **PURPOSE OF MEETING:** | | ENV Status Update | | |
| **ATTENDEES:** | | PD: John Tyler, Jake Powell, Steven Tate  RKCI: Brittney Davis | | |
| **FROM:** | | John Tyler, P.E., RAS | **PROJECT NO.:** | 12775-00 |

**DISCUSSION:**

**Schedule- Current design schedule (dependent of AFA)**

* DCC – 4/2022 based on TxDOT’s ability to participate due to AFA status
* 30% DDRT / Schematic – 05/2023- Full TxDOT schematic
* 60% DDRT – 09/2023- Following TxDOT procedures may require PDCC (pavement design review) and DSRT (safety review) at the 30% or 60% level.
* 90% DDRT – 112/2023 (Hold plans during ROW / Utility)- Shown as 100% in contract, plans ready to let but there will be ~14 month period for ROW acquisition, utility relocations, etc. Certification will not be ready until utilities and ROW are clear.
* Final Plans – 4/2025- 8/2025 letting, final plans 5 months prior to being let.

**Project Development Updates**

* ROE on-going. CoS sent project introduction letters to residents.
* SharePoint site created with ROE tracking information- Access needed?
* Initial traffic projections complete, submitted to TxDOT for review (waiting of AFA)
* Geotechnical field investigations complete, laboratory
* Topographic survey complete
* Existing ROW resolution and mapping 99% complete, final deliverable next week
* Evaluated alignment alternatives
* Development of preliminary typical sections
* Conducted geometric workshop with CoS and Guadalupe County
  + Preliminary schematic and alternatives available

**TxDOT Environmental Initiation**

* TxDOT ECOS documentation for TxDOT
  + What information is necessary to complete this process
  + What can be done now?

**Environmental Document**

* CE vs EA
  + Technical differences
  + Schedule impacts
* ROW impacts
  + Preferred alignment shown in preliminary layout has the following
    - 48 impacted parcels
    - ~24 AC of acquisition
  + Alternative of interest
    - ~33 AC
    - Potential for donation of existing ROW
* Conservation easements
  + Unknown at Big Red Barn and electrical sub-station
  + Impact to ENV document?
  + RKCI have the ability to determine conservation easements?

**END OF MEMO**

P:\127\75\00\ProjectData\MeetingMinutes\230210- ENV update\230210\_Cordova\_ENV\_Status.docx