|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **MEETING TITLE:** | City of Seguin – Cordova Rd Reconstruction  TxDOT DCC June | | **DATE:** | 06/01/2023 | | |
| **PROJECT NUMBER:** | 0915-46-052 | |  |  | | |
| **Attendees:** | See TxDOT Sign in - Teams Meeting | |  |  | | |
| **AGENDA TOPICS:** | | | | | |
| Cordova Rd | | Project Overview:   * Partnership with City and County * Off system 2-Lane expansion to 4 lane divided with raised center median and dual SUP with combination of roadside swales and closed conduit   Schedule:   * DCC – June * DDRT – 30% Schematic July 2023 * DDRT – 60% PS&E November 2023 * 90% PS&E Review March 2024 * Pause for utility relocation and ROW   + March 2024 – May 2025 * Final plans/letting Q4 2025 * Construction schedule pending   + Letting Nov 2025   Environmental:   * Preliminary scope review and kickoff with John Bryant 05/16   + Preparing for ECOS * Historical review * Public meetings with key stakeholders on going   + Big Red Barn   + Developers   + GVEC * ROW Acquisition of numerous parcels mostly large residential lots and agricultural land   + No identified displacements | | | |
|  | | Utility Coordination:   * Ongoing; majority identified * SUE Level B-D Complete * NOPC Pending   Project Coordination   * SH 46   + Official comment from public meeting * SH 123 | | | |
|  | | | | |
| **ACTION ITEMS & TAKEAWAYS:**  **Description** | | | | | |
|  | | | | | |