| MEETING TITLE: | City of Seguin – Cordova Rd Reconstruction TxDOT DCC June |  | DATE: | 06/01/2023 |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| PROJECT NUMBER: | 0915-46-052 |  |  |  |  |  |
| Attendees: | See TxDOT Sign in - Teams Meeting |  |  |  |  |  |
| AGENDA TOPICS: |  |  |  |  |  |
| Cordova Rd |  | Project Overview: - Partnership with City and County - Off system 2-Lane expansion to 4 lane divided with raised center median and dual SUP with combination of roadside swales and closed conduit Schedule: - DCC – June - DDRT – 30% Schematic July 2023 - DDRT – 60% PS&E November 2023 - 90% PS&E Review March 2024 - Pause for utility relocation and ROW - March 2024 – May 2025 - Final plans/letting Q4 2025 - Construction schedule pending - Letting Nov 2025 Environmental: - Preliminary scope review and kickoff with John Bryant 05/16 - Preparing for ECOS - Historical review - Public meetings with key stakeholders on going - Big Red Barn - Developers - GVEC - ROW Acquisition of numerous parcels mostly large residential lots and agricultural land - No identified displacements |  |  |  |
|  |  | Utility Coordination: - Ongoing; majority identified - SUE Level B-D Complete - NOPC Pending Project Coordination - SH 46 - Official comment from public meeting - SH 123 |  |  |  |
| ACTION ITEMS & TAKEAWAYS: Description |  |  |  |  |  |