|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **MEETING TITLE:** | City of Seguin – Cordova Rd Reconstruction  TxDOT DCC June | | **DATE:** | 06/01/2023 | |
| **PROJECT NUMBER:** | 0915-46-052 | |  |  | |
| **Attendees:** | See TxDOT Sign in - Teams Meeting | |  |  | |
| **DCC Meeting Minutes** | | | | |
| Cordova Rd | | * MPO Funding   + There is potential for additional federal funding to help with overruns   + MPO STBG call for overrun needs after TIP is adopted * Schedule   + TxDOT has slightly different design schedule on file   + PD/CoS to supply latest and TxDOT to update internally * ROW   + LG must follow Uniform Act for ROW acquisition * Environmental   + TxDOT’s SH 123 project did not find jurisdiction wetlands at the Cordova/SH 123 intersection   + CoS’ consultant to confirm and clear wetlands for remainder of project   + Identifying 4F/historical properties within the project is critical to identify early * Public Involvement   + Public meeting desired after 30% design   + TxDOT internal coordination for planning of public involvement   + CoS/Consultant to provide timeline to TxDOT for public meeting * Utilities   + TxDOT requested utility construction schedule when available * Roadway   + With the use of curb & gutter TxDOT suggests the minimum roadway slope may be reduced to 0.35%   + TxDOT to provide comments on layout | | |
|  | | * Drainage   + If there is difficulty funding overruns; drainage criteria could be reduced from City design requirements to match design TxDOT requirements   + TxDOT stated LG off-system projects can be designed to existing drainage conveyance or better   + Current design event for cross culverts is 25-year   + TxDOT requested drainage review meeting prior to 30% DDRT   + TxDOT stated there is a drainage report for the TxDOT SH 123 project. The Cordova Rd project should complement the SH 123 drainage design.   + Drainage sheets to follow SAT District format * Pavement Design   + TxDOT requested the pavement design report be sent to jose.emilio.ramos@txdot.gov * DSRT   + The need for a DSRT will be determined at a later date * Letting Date   + Letting moving to FY 2026   + CoS to supply request to amend TIP * TxDOT/CoS to coordinate with MPO | | |
|  | | | | |