| MEETING TITLE: | City of Seguin – Cordova Rd Reconstruction TxDOT DCC June |  | DATE: | 06/01/2023 |  |
| --- | --- | --- | --- | --- | --- |
| PROJECT NUMBER: | 0915-46-052 |  |  |  |  |
| Attendees: | See TxDOT Sign in - Teams Meeting |  |  |  |  |
| DCC Meeting Minutes |  |  |  |  |
| Cordova Rd |  | - MPO Funding - There is potential for additional federal funding to help with overruns - MPO STBG call for overrun needs after TIP is adopted - Schedule - TxDOT has slightly different design schedule on file - PD/CoS to supply latest and TxDOT to update internally - ROW - LG must follow Uniform Act for ROW acquisition - Environmental - TxDOT’s SH 123 project did not find jurisdiction wetlands at the Cordova/SH 123 intersection - CoS’ consultant to confirm and clear wetlands for remainder of project - Identifying 4F/historical properties within the project is critical to identify early - Public Involvement - Public meeting desired after 30% design - TxDOT internal coordination for planning of public involvement - CoS/Consultant to provide timeline to TxDOT for public meeting - Utilities - TxDOT requested utility construction schedule when available - Roadway - With the use of curb & gutter TxDOT suggests the minimum roadway slope may be reduced to 0.35% - TxDOT to provide comments on layout |  |  |
|  |  | - Drainage - If there is difficulty funding overruns; drainage criteria could be reduced from City design requirements to match design TxDOT requirements - TxDOT stated LG off-system projects can be designed to existing drainage conveyance or better - Current design event for cross culverts is 25-year - TxDOT requested drainage review meeting prior to 30% DDRT - TxDOT stated there is a drainage report for the TxDOT SH 123 project. The Cordova Rd project should complement the SH 123 drainage design. - Drainage sheets to follow SAT District format - Pavement Design - TxDOT requested the pavement design report be sent to jose.emilio.ramos@txdot.gov - DSRT - The need for a DSRT will be determined at a later date - Letting Date - Letting moving to FY 2026 - CoS to supply request to amend TIP - TxDOT/CoS to coordinate with MPO |  |  |