|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **MEETING TITLE:** | City of Seguin – Cordova Rd Reconstruction  Traffic Projection Review Meeting | | **DATE:** | 07/05/2023 | |
| **PROJECT NUMBER:** | 0915-46-052 | |  |  | |
| **Attendees:** | TxDOT: Scott Nelson, Chip Perry, Eddie Gonzalez  City of Seguin: Pablo Martinez  Pape-Dawson: John Tyler, Justin Clark, Jake Powell, Steven Tate | |  |  | |
| **AGENDA TOPICS:** | | | | |
| Cordova Rd | | Project Overview:   * Limits: SH 46 to SH 123 * Partnership with City and County * Off system 2-Lane expansion to 4 lane divided with raised center median and dual SUP with combination of roadside swales * AFA now fully executed.   Schedule:   * DCC – June (Complete) * DDRT – 30% August 2023 * DDRT – 60% November 2023 * 90% March 2024 * Pause for utility relocation and ROW * Final plans/letting Q4 2025   Traffic Projections   * Option C   + **TxDOT agreed projections will be Option C and approved by District** * Review of memo   + **TxDOT requested memo be uploaded to Bluebeam and a link be provided. TxDOT to review/meet internally.** | | |
|  | | * **PD explained methodology and background growth percentage of 5%**   + **TxDOT agreed with methodology and growth percentage** * **TxDOT requested base year be updated to opening year instead of letting year.** * **TxDOT to provide SH 46 project traffic projection data** | | |