| MEETING TITLE: | City of Seguin – Cordova Rd Reconstruction Traffic Projection Review Meeting |  | DATE: | 07/05/2023 |  |
| --- | --- | --- | --- | --- | --- |
| PROJECT NUMBER: | 0915-46-052 |  |  |  |  |
| Attendees: | TxDOT: Scott Nelson, Chip Perry, Eddie Gonzalez City of Seguin: Pablo Martinez Pape-Dawson: John Tyler, Justin Clark, Jake Powell, Steven Tate |  |  |  |  |
| AGENDA TOPICS: |  |  |  |  |
| Cordova Rd |  | Project Overview: - Limits: SH 46 to SH 123 - Partnership with City and County - Off system 2-Lane expansion to 4 lane divided with raised center median and dual SUP with combination of roadside swales - AFA now fully executed. Schedule: - DCC – June (Complete) - DDRT – 30% August 2023 - DDRT – 60% November 2023 - 90% March 2024 - Pause for utility relocation and ROW - Final plans/letting Q4 2025 Traffic Projections - Option C - TxDOT agreed projections will be Option C and approved by District - Review of memo - TxDOT requested memo be uploaded to Bluebeam and a link be provided. TxDOT to review/meet internally. |  |  |
|  |  | - PD explained methodology and background growth percentage of 5% - TxDOT agreed with methodology and growth percentage - TxDOT requested base year be updated to opening year instead of letting year. - TxDOT to provide SH 46 project traffic projection data |  |  |