| MEETING TITLE: | City of Seguin – Cordova Rd Reconstruction Lassig Farms Coordination |  | DATE: | 07/06/2023 |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| PROJECT NUMBER: | 12775-00 |  |  |  |  |  |
| Attendees: | PD: Steven Tate, John Tyler Colliers: Wayne Flores |  |  |  |  |  |
| AGENDA TOPICS: |  |  |  |  |  |
| Cordova Rd |  | All discussion items are subject to final CoS approval Schedule: - Design; Now through Q1 2024 - Pause for utility relocation and ROW - Final plans/letting Q4 2025/Q1 2026 - Construction schedule pending Scope - Full reconstruction - Expand from 2 to 4 lanes with raised median - Dual shared use paths - Minimum of 120’ ROW |  |  |  |
| Reinhard Farms |  | Project Status - Design and construction schedule - Platting, ROW dedication timeline, lot status - ROW/Lot linework - Developer and home builder? - Association with Lily Springs/Connection to SH 46 - TIA; - Eastbound left turn warranted- Assumed delay until Unit 2- Proximity to ultimate SH 46 intersection - West right turn is warrant- assumed delayed or included with Cordova via developer agreement. - Detention - Linework needed - Utilities - Extension from Cordova corridor or Lily Springs? |  |  |  |
| ACTION ITEMS & TAKEAWAYS: Description |  |  |  |  |  |