| MEETING TITLE: |  | City of Seguin – Cordova Rd Reconstruction TROE Update | DATE: | 07/07/2023 |  |
| --- | --- | --- | --- | --- | --- |
| PROJECT NUMBER: |  | 0915-46-052 |  |  |  |
| Attendees: |  | City of Seguin: Connie Real Pape-Dawson: John Tyler, Jake Powell, Steven Tate Pinnacle: Daniel Shaw |  |  |  |
| AGENDA TOPICS: |  |  |  |  |
| TROE | - ROE update - 89 total ROE letters sent - 65 signed letters received (73%) - 24 ROE letters outstanding - Outstanding ROE for impacted parcels are critical |  |  |  |
| Outstanding ROE | Impacting 48 parcels Missing 9 TROE for impacted parcels 2- unidentified for TROE– Cordova Crossing easements - Pinnacle to verify in TROE was sent, other Cordova Crossing TROE have been executed. Parcel numbers; 183340,178053 Strategy to obtain missing TROE - Review missing parcels - Unresponsive or contentious - Parcel 55539- Mr Sanchez and family are Spanish speaking and need translation. Pinnacle to provide translation and coordinate meeting - Parcels 148684, 148683, 148682, 148681- Mr. Valdez would like field meeting with more project specific information. Pinnacle to coordinate meeting - Parcel 55572- Ms Cranford has attorney. Pinnacle to attempt contact with Troy Burch. File with court to obtain entry if progress is not made. - Parcel 55521- Owner in bad health. Pinnacle to attempt contact one final time then file in court if no response. - Parcel 55163- Several attempts made by CoS. File with court. - Parcel 83116- Pinnacle to attempt to schedule field meeting - Parcel 55918- ROW to be dedicated with future development. CoS to determine if dedication can be required and conformance with Uniform Act. Beginning Survey/ROE - 48 parcels to survey Process/order - Pinnacle to mail letter stating that entry will be upcoming within date range and explanation that it will be survey operation to locate property corners. - PD surveyors will contact owner and schedule/notify prior to entering and meet any special provisions. Pinnacle to provide spreadsheet with contact information/special provisons Open Discussion - Filing with court needs to occur ASAP for any necessary parcel. Process will take ~30-45 days - Pinnacle to coordinate process and filing with CoS - Existing TROE expire 12/2023 - CoS confirmed schematic can be shared - CoS requested separate outreach to Mr Urban prior to entering property |  |  |  |